## Taul1
Work tracking sheet |  |  |  | Name: | NHAM DIEN TRAN
|  |  |  | Signature: | TRAN NHAM
Date | Time IN | Time OUT | Time today | Sum. Time | Activities
2017-11-28 |  |  | 6 hours | 6 | Decide Q1 interface and research for the js coding
2017-11-29 |  |  | 3 hours | 9 | Make HTML file and find a cool tab's transition css, also finish Q1.
31/11/17 |  |  | 2 hours | 11 | Group discuss for the UI ideas, debug Q1
2017-12-06 |  |  | 3 hours | 14 | Doing JS and HTML for Q2 based on Q1 converter, but got trouble in making new rows
2017-12-08 |  |  | 3 hours | 17 | Research and doing the JS code to create new elements of <tr> and <td>
2017-12-09 |  |  | 4 hours | 21 | Add the show/hide button with toggle text, debug Q2 and showing the incorrect input notice.
2017-12-12 |  |  | 4 hours | 25 | Doing JS and HTML for Q3-combinatorics
2017-12-13 |  |  | 3 hours | 28 | Moving to Q4-truth table and research but have gave up…
2017-12-14 |  |  | 3 hours | 31 | Adding up the formula's images for Q3, moving to Q5 and do the JS code for it
2017-12-15 |  |  | 4 hours | 35 | Finding out how to print JS into HTML for Q5 (array - table layer)
2017-12-16 |  |  | 6 hours | 41 | Adding up to Q5 the showing of random tests, and have figured out to do the truth table
2017-12-17 |  |  | 9 hours | 50 | Finishing Q4 and add a slide "About the project" and make JS code to make it default tab and finishing edit CSS